## Gantt Chart Template
Task name | Start date | End date | Assigned | Status | 2023-04-13 | 2023-01-27 | 2023-03-17 | 2023-04-07 | 2023-03-02 | 2023-03-24 | 2023-02-06 | 2023-04-21 | 2023-04-22 | 2023-04-23 | 2023-04-24 | 2023-03-09 | 2023-04-04 | 2023-04-06 | 2023-04-13 | 2020-02-10 | 2020-02-11 | 2020-02-12 | 2020-02-13 | 2020-02-14 | 2020-02-15 | 2020-02-16 | 2020-02-17 | 2020-02-18 | 2020-02-19 | 2020-02-20 | 2020-02-21 | 2020-02-22 | 2020-02-23 | 2020-02-24 | 2020-02-25 | 2020-02-26 | 2020-02-27 | 2020-02-28 | 2020-03-01 | 2020-03-02 | 2020-03-03 | 2020-03-04 | 2020-03-05 | 2020-03-06 | 2020-03-07
Team Pong | 2023-01-01 | 2023-04-13 | Team | Done
Software Requirements | 2023-01-13 | 2023-01-27 | Dominic | Closed
Hardware Requirements | 2023-01-14 | 2023-03-17 | Ian | Closed
Budget | 2023-01-15 | 2023-04-07 | Dominic | Closed
Scheduling | 2023-01-17 | 2023-04-13 | Aditya | Closed
Software For Pong | 2023-01-25 | 2023-03-02 | Dominic | Done
Order for the parts required | 2023-02-06 | 2023-03-24 | Ian | Done
PDR | 2023-02-06 | 2023-02-06 | Team | Done
LCD and management | 2023-02-20 | 2023-04-21 | Drew | Closed
Testing the components | 2023-02-27 | 2023-04-22 | Aditya | Done
LCD and Software | 2023-03-06 | 2023-04-23 | Dominic | Done
Case Unit model | 2023-03-13 | 2023-04-24 | Ian | Done
CDR | 2023-03-09 | 2023-03-09 | Team | Done
Expo Presentation | 2023-03-27 | 2023-04-04 | Team | Done
Final Budget | 2023-04-03 | 2023-04-06 | Drew | Done
Last Test | 2023-04-10 | 2023-04-13 | Team | Done

## Assignees and Status
Assignees | Status
Aditya | Open
Ian | In process
DRew | Closed
Dominic | Done